## Admin
S.No | Bug ID | Title/Summary | Description | Module/Screen | Pre-Conditions | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Browser / Device Details | Tested By
1 | ADM-001 | Dashboard UI alignment issues | Multiple dashboard cards, widgets and sections are misaligned, affecting the overall UI appearance. | Admin → Dashboard | User logged in as Admin. | 1. Login as Admin. 2. Navigate to Dashboard. | All dashboard components should be properly aligned. | Multiple UI alignment issues are observed. | Medium | Medium | Microsoft Edge, Chrome | Nikhitha
2 | ADM-002 | Dashboard and Dashboard Templates remain selected simultaneously | When Dashboard Templates is selected, both Dashboard and Dashboard Templates remain highlighted. | Admin → Navigation | User logged in. | 1. Open Dashboard. 2. Click Dashboard Templates. | Only the selected menu should remain highlighted. | Both menus remain highlighted simultaneously. | Medium | Medium | Microsoft Edge, Chrome | Nikhitha
3 | ADM-003 | Dashboard labels have inconsistent capitalization | Labels such as Revenue Pipeline, Lead Funnel and Activity Mix are displayed with inconsistent capitalization. | Admin → Dashboard | User logged in. | Open Dashboard. | Menu labels should follow consistent capitalization. | Menu labels appear with inconsistent capitalization. | Low | Low | Microsoft Edge, Chrome | Nikhitha
4 | ADM-004 | Executive Overview alignment issues | Widgets and sections under Executive Overview are not properly aligned. | Admin → Executive Overview | User logged in. | Open Executive Overview. | Widgets should be properly aligned. | Several alignment issues are observed. | Medium | Medium | Microsoft Edge, Chrome | Nikhitha
5 | ADM-005 | Twitter logo missing in Platform-wise Engagement | The Twitter/X icon is not displayed in the Platform-wise Engagement section. | Admin → Executive Overview | User logged in. | Open Executive Overview and navigate to Platform-wise Engagement. | Twitter/X logo should be displayed correctly. | The Twitter/X logo is missing. | Low | Medium | Microsoft Edge, Chrome | Nikhitha
6 | ADM-006 | Platform-wise Engagement alignment issues | UI components under Platform-wise Engagement are misaligned. | Admin → Executive Overview | User logged in. | Open Platform-wise Engagement. | All UI components should be aligned properly. | Multiple alignment issues are observed. | Medium | Medium | Microsoft Edge, Chrome | Nikhitha
7 | ADM-007 | Engagement Trend graph rendering issue | The Engagement Trend graph is distorted and difficult to interpret. | Admin → Campaign Performance | User logged in. | Open Campaign Performance. | Graph should render correctly. | Graph appears irregular and distorted. | Medium | Medium | Microsoft Edge, Chrome | Nikhitha
8 | ADM-008 | Customer Intelligence alignment issues | Customer Satisfaction and Brand Sentiment sections have alignment issues. | Admin → Customer Intelligence | User logged in. | Open Customer Intelligence. | UI components should be aligned properly. | Several alignment issues are observed. | Medium | Medium | Microsoft Edge, Chrome | Nikhitha
9 | ADM-009 | Rolling Brand Sentiment Trend graph rendering issue | The Rolling Brand Sentiment Trend graph appears distorted and visually inconsistent. | Admin → Customer Intelligence | User logged in. | View Rolling Brand Sentiment Trend. | Graph should render correctly. | Graph appears distorted. | Medium | Medium | Microsoft Edge, Chrome | Nikhitha
10 | ADM-010 | Poor color contrast in Customer Intelligence graphs | The graph colors reduce readability and make data difficult to understand. | Admin → Customer Intelligence | User logged in. | View graph section. | Graphs should have proper color contrast. | Graph colors are difficult to read. | Low | Medium | Microsoft Edge, Chrome | Nikhitha
11 | ADM-011 | My Follow-ups status alignment issue | Status dropdown and related fields are misaligned. | Admin → My Day → My Follow-ups | User logged in. | Open My Follow-ups. | Status dropdown should be properly aligned. | Status field and dropdown are misaligned. | Medium | Medium | Microsoft Edge, Chrome | Nikhitha
12 | ADM-012 | Sales Monitor alignment issues | Several Sales Monitor widgets are misaligned. | Admin → Monitoring → Command Center | User logged in. | Open Command Center. | Widgets should be properly aligned. | Widgets appear misaligned. | Medium | Medium | Microsoft Edge, Chrome | Nikhitha
13 | ADM-013 | Forecast Pipeline values are partially hidden | Numeric values in Forecast Pipeline are partially hidden due to UI issues. | Admin → Monitoring → Command Center | User logged in. | Open Forecast Pipeline. | All values should be fully visible. | Numbers are partially hidden. | Medium | Medium | Microsoft Edge, Chrome | Nikhitha
14 | ADM-014 | Command Center UI alignment issues | Several UI elements in Command Center are not properly aligned. | Admin → Monitoring → Command Center | User logged in. | Open Command Center. | UI should be properly aligned. | Alignment issues are observed. | Medium | Medium | Microsoft Edge, Chrome | Nikhitha
15 | ADM-015 | Left navigation panel scrolls with page | The left navigation panel scrolls together with the page instead of remaining fixed. | Common UI | User logged in. | Scroll any page. | Navigation panel should remain fixed while scrolling. | Navigation panel scrolls with page content. | Medium | Medium | Microsoft Edge, Chrome | Nikhitha
16 | ADM-016 | Attendance Approval status text formatting issue | The "No Longer" status text appears poorly formatted and affects readability. | Admin → Attendance Approval | User logged in. | Open Attendance Approval. | Status text should be clearly displayed. | No Longer text appears visually inconsistent. | Low | Low | Microsoft Edge, Chrome | Nikhitha
17 | ADM-017 | View Map displays incorrect employee location | Clicking View Map displays an incorrect location that does not match the employee's actual location. | Admin → Attendance Approval | User logged in. | 1. Open Attendance Approval. 2. Click View Map. | Map should display the employee's correct recorded location. | Map displays an incorrect location. | High | High | Microsoft Edge, Chrome | Nikhitha
18 | ADM-018 | Leave Type alignment issues | Leave Type values are misaligned, affecting readability. | Admin → Leave Approval | User logged in. | Open Leave Approval. | Leave Type values should be properly aligned. | Alignment issues are observed. | Low | Medium | Microsoft Edge, Chrome | Nikhitha
19 | ADM-019 | Leave Calendar has poor color contrast | The Leave Calendar uses dark colors that reduce the visibility of approved leaves and filters. | Admin → Leave Calendar | User logged in. | Open Leave Calendar. | Calendar should use readable colors with sufficient contrast. | Text and filters are difficult to read due to poor color contrast. | Medium | Medium | Microsoft Edge, Chrome | Nikhitha
20 | ADM-020 | Upcoming Holidays text visibility and alignment issues | Holiday names are difficult to read due to poor colors, and several holiday entries are misaligned. | Admin → Upcoming Holidays | User logged in. | Open Upcoming Holidays. | Holiday names should be clearly visible and properly aligned. | Text visibility is poor and alignment issues are observed. | Medium | Medium | Microsoft Edge, Chrome | Nikhitha
21 | ADM-021 | Attendance Report accepts invalid date range | Attendance Report allows invalid date combinations and lacks proper validation. | Admin → Attendance Report | User logged in as Admin. | 1. Open Attendance Report. 2. Select invalid From Date and To Date. | System should validate the selected date range. | Application accepts invalid date combinations. | Medium | High | Microsoft Edge, Chrome | Nikhitha
22 | ADM-022 | Communication Log filter alignment issues | From Date, To Date and filter fields are misaligned and partially hidden. | Admin → Communications Log | User logged in. | Open Communications Log. | All filter fields should be properly aligned and visible. | Fields are misaligned and partially hidden. | Medium | Medium | Microsoft Edge, Chrome | Nikhitha
23 | ADM-023 | Communication Log accepts unsupported attachment format | Proof Screenshot upload accepts PDF files instead of restricting to image formats (if image upload is the intended requirement). | Admin → Communications Log | User logged in. | Upload a PDF file as Proof Screenshot. | System should accept only supported image formats (if required). | Application accepts PDF files. | Medium | Medium | Microsoft Edge, Chrome | Nikhitha
24 | ADM-024 | Outcome and Notes fields accept unrestricted special characters | Outcome and Notes fields accept only special characters without validation. | Admin → Communications Log | User logged in. | Enter only special characters in Outcome and Notes. | System should validate the entered values according to business rules. | Application accepts invalid input. | Low | Medium | Microsoft Edge, Chrome | Nikhitha
25 | ADM-025 | Happened At field accepts future dates | Happened At field allows future dates and saves the record successfully. | Admin → Communications Log | User logged in. | Select a future date and save. | Future dates should be restricted unless allowed by business requirements. | Application accepts future dates. | Medium | High | Microsoft Edge, Chrome | Nikhitha
26 | ADM-026 | Meetings & Demos alignment issues | Date and Time fields are misaligned and partially hidden. | Admin → Meetings & Demos | User logged in. | Open Meetings & Demos. | Fields should be properly aligned and visible. | UI alignment issues observed. | Medium | Medium | Microsoft Edge, Chrome | Nikhitha
27 | ADM-027 | Meetings & Demos accepts invalid date range | The module allows invalid past/future date combinations without validation. | Admin → Meetings & Demos | User logged in. | Select invalid dates and save. | Application should validate the selected dates. | Application accepts invalid dates. | Medium | High | Microsoft Edge, Chrome | Nikhitha
28 | ADM-028 | Task Title accepts invalid characters | Task Title field accepts numbers and special characters without validation. | Admin → Task Board → Assign Task | User logged in. | Enter invalid Task Title and save. | Task Title should validate input. | Application accepts invalid Task Title. | Medium | Medium | Microsoft Edge, Chrome | Nikhitha
29 | ADM-029 | Task Board accepts invalid date range | Start Date and Deadline accept invalid date combinations. | Admin → Task Board | User logged in. | Select invalid Start Date and Deadline. | Application should validate dates. | Application accepts invalid date combinations. | Medium | High | Microsoft Edge, Chrome | Nikhitha
30 | ADM-030 | Task Description accepts special characters | Description field accepts unrestricted special characters. | Admin → Task Board | User logged in. | Enter only special characters in Description. | Description should validate input. | Application accepts invalid input. | Low | Medium | Microsoft Edge, Chrome | Nikhitha
31 | ADM-031 | Performance dashboard alignment issues | Several widgets and cards in the Performance dashboard are misaligned. | Admin → Performance | User logged in. | Open Performance dashboard. | Widgets should be properly aligned. | Multiple alignment issues are observed. | Medium | Medium | Microsoft Edge, Chrome | Nikhitha
32 | ADM-032 | Generate Invoice returns 403 error | Generate Invoice action fails with a 403 Access Denied error. | Admin → Finance → Invoicing | User logged in. | Click Generate Invoice. | Invoice should be generated successfully. | Application displays 403 Access Denied. | High | High | Microsoft Edge, Chrome | Nikhitha
33 | ADM-033 | Invoice Status filter is incomplete | Status dropdown displays only Unpaid and Overdue options. | Admin → Finance → Invoicing | User logged in. | Click Status filter. | All configured statuses should be available. | Only Unpaid and Overdue options are displayed. | Medium | Medium | Microsoft Edge, Chrome | Nikhitha
34 | ADM-034 | Update Social Stats returns 403 Access Denied | Update Social Stats page displays 403 Access Denied. | Admin → Marketing → Update Social Stats | User logged in. | Open Update Social Stats. | Page should open successfully. | Application displays 403 Access Denied. | High | High | Microsoft Edge, Chrome | Nikhitha
35 | ADM-035 | Marketing Performance page alignment issues | The Marketing Performance page contains inconsistent fonts, colors, spacing and alignment. | Admin → Marketing → Performance | User logged in. | Open Marketing Performance. | UI should be consistent and properly aligned. | Multiple alignment issues are observed. | Medium | Medium | Microsoft Edge, Chrome | Nikhitha
36 | ADM-036 | Today's Updates and Pending Updates overlap | The Today's Updates and Pending Updates sections overlap, making the content difficult to read. | Admin → Marketing → Performance | User logged in. | Open Marketing Performance. | Sections should be displayed separately with proper spacing. | Sections overlap each other. | Medium | Medium | Microsoft Edge, Chrome | Nikhitha
37 | ADM-037 | Social Configuration panel alignment issues | Social Configuration panel and Assigned Social Account panel are misaligned and not properly arranged. | Admin → Marketing → Social Configuration | User logged in. | Open Social Configuration. | Panels should be properly aligned with consistent spacing. | Panels are misaligned and appear shifted. | Medium | Medium | Microsoft Edge, Chrome | Nikhitha
38 | ADM-038 | Reports page alignment issues | Planned Payment filter and related fields are misaligned, causing some text and controls to be partially hidden. | Admin → Reports | User logged in. | Open Reports module. | All report filters should be properly aligned and visible. | Planned Payment field and controls are partially hidden. | Medium | Medium | Microsoft Edge, Chrome | Nikhitha
39 | ADM-039 | Employee details are not visible when selecting Employee ID | Selecting an Employee ID changes the details to a white color, making the content unreadable. | Admin → HR & Payroll | User logged in. | Select an Employee ID. | Selected employee details should remain clearly visible. | Employee details become white and unreadable. | High | High | Microsoft Edge, Chrome | Nikhitha
40 | ADM-040 | HR Dashboard has poor color contrast and alignment issues | HR Dashboard uses poor color combinations and contains multiple alignment issues. Several widgets appear in a zigzag layout, making the dashboard difficult to read. | Admin → HR Dashboard | User logged in. | Open HR Dashboard. | Dashboard should have proper alignment and readable colors. | Dashboard has poor color contrast and multiple alignment issues. | Medium | Medium | Microsoft Edge, Chrome | Nikhitha
41 | ADM-041 | HRMS Report has color and alignment issues | HRMS Report contains poor color contrast and multiple alignment issues that affect readability. | Admin → HRMS Report | User logged in. | Open HRMS Report. | Report should have readable colors and proper alignment. | Report contains poor colors and alignment issues. | Medium | Medium | Microsoft Edge, Chrome | Nikhitha
42 | ADM-042 | Payroll Structure page has multiple UI alignment issues | Several controls, labels and sections in Payroll Structure are misaligned. | Admin → Payroll Structure | User logged in. | Open Payroll Structure. | All fields should be properly aligned. | Multiple alignment issues are observed. | Medium | Medium | Microsoft Edge, Chrome | Nikhitha
43 | ADM-043 | Payroll Runs displays future months as processed | Future payroll months appear in Payroll Runs before the payroll period is reached. | Admin → Payroll Runs | User logged in. | Open Payroll Runs and observe previous runs. | Future payroll months should not appear as processed unless permitted by business rules. | Future months are displayed in Payroll Runs. | High | High | Microsoft Edge, Chrome | Nikhitha
44 | ADM-044 | My Payslips displays future payroll records | My Payslips displays payslips for future payroll periods that are not yet due. | Admin → My Payslips | User logged in. | Open My Payslips. | Only available payroll periods should be displayed. | Future payroll periods are displayed. | High | High | Microsoft Edge, Chrome | Nikhitha

## Hr
S.No | Bug ID | Title/Summary | Description | Module/Screen | Pre-Conditions | Steps to reproduce | Expected Result | Actual Result | Severity | Priority | Browser / Device Details | Tested By
1 | BUG_HR1 | Employee ID field accepts invalid special characters. | The Employee ID field allows users to enter only special characters such as @@@@, which should not be permitted if Employee IDs are expected to be alphanumeric. | Employee Management → Add Employee | User is on the Add Employee form. | 1. Enter @@@@ in the Employee ID field. 2. Save the employee details.. | Only valid Employee IDs (e.g., alphanumeric) should be accepted. | The field accepts only special characters. | Medium | Medium
2 | BUG_HR2 | Email Address field accepts invalid email format | The Email Address field accepts invalid email formats without proper validation. Users can enter malformed email addresses and the application allows submission without displaying any validation error. | Employee Management → Add Employee | User is logged into the application. User navigates to Add Employee. | Open the Add Employee form. Enter an invalid email such as abc@gmail (without a valid domain extension) or abc@@gmail.com. Fill the remaining mandatory fields. Click Save/Submit. | The application should reject invalid email formats and display a validation message such as "Please enter a valid email address." | The application accepts invalid email formats and allows the record to be saved without validation. | Medium | High
3 | BUG_HR3 | Mobile Number field accepts dummy/repetitive values | The Mobile Number field validates only the length and starting digit (6–9). However, it accepts dummy or repetitive numbers such as 6000000000, which are not meaningful mobile numbers. The application does not validate the quality of the entered data. |  | User is logged into the application. User is on the Add Employee page. | Open Add Employee. Enter 6000000000 in the Mobile Number field. Fill the remaining mandatory fields. Click Save. | The application should reject dummy or repetitive mobile numbers and display an appropriate validation message. | The application accepts 6000000000 as a valid mobile number.
4 | BUG_HR4 | Aadhaar Number field accepts invalid dummy values (e.g., 000000000000). | The Aadhaar Number field validates only the 12-digit length but accepts dummy values such as 000000000000 without any additional validation. |  | User is logged into the application. User is on the Add Employee page. | Enter 000000000000 in the Aadhaar Number field. Fill the remaining mandatory fields. Click Save. | The application should reject invalid or dummy Aadhaar numbers. | The application accepts 000000000000 as a valid Aadhaar Number.
5 | BUG_HR5 | Bank Account Number field accepts dummy values consisting only of zeros. | The Account Number field validates only the numeric format and length but accepts invalid values such as 0000000000000000. |  | User is on the Bank Details page. | Enter 0000000000000000 in the Account Number field. Fill the remaining mandatory fields. Click Save. | The application should reject dummy account numbers. | The application accepts the dummy account number.
6 | BUG_HR6 | Confirm Account Number accepts dummy account numbers without validation. | The Confirm Account Number field accepts dummy values when they match the Account Number. The application validates only whether both fields match and does not validate whether the entered account number itself is meaningful. |  | User is on the Bank Details page. | Enter 0000000000000000 in the Account Number field. Enter the same value in Confirm Account Number. Click Save. | The application should reject invalid account numbers even if both fields match. | The application accepts matching dummy account numbers.
7 | BUG_HR7 | UAN Number field accepts invalid dummy values | The UAN Number field validates only the required number of digits but accepts dummy values such as 000000000000. |  | User is on the Employee Details page. | Enter 000000000000 in the UAN Number field. Fill the remaining mandatory fields. Click Save. | The application should reject dummy or invalid UAN numbers. | The application accepts the dummy UAN Number.
8 | BUG_HR8 | Poor color contrast affects chart readability and overall UI visibility. | Several charts, graphs, and UI components use overly bright or low-contrast colors, making the displayed information difficult to read and understand. The current color combinations negatively impact visibility and overall user experience. | HRMS Dashboard, HRM REPORTS | User is logged into the application. User navigates to the Dashboard/Analytics page (or the affected module). | Log in to the application. Navigate to the Dashboard/Analytics screen. Observe the colors used in charts, graphs, cards, and other UI components. Compare the visibility of labels, legends, and chart data. | The application should use colors with sufficient contrast to ensure charts, graphs, and UI elements are clearly visible and easily readable. | Some UI elements use overly bright or low-contrast colors, making labels, chart values, and graphical information difficult to read.
9 | BUG_HR9 | UI elements are misaligned across multiple screens. | Several UI components, including text fields, labels, buttons, cards, tables, and sections, are not properly aligned. The inconsistent spacing and positioning create a zigzag appearance, reducing the overall visual consistency and professionalism of the application. | Dashboard / Employee Management / Multiple Screens | User is logged into the application. User navigates to the affected screens. | Log in to the application. Navigate through different modules/screens. Observe the alignment of text, labels, buttons, cards, tables, and other UI elements. | All UI components should be consistently aligned with proper spacing and positioning, following the application's design guidelines. | Multiple UI elements are misaligned, resulting in inconsistent spacing and a zigzag layout that affects the overall user experience. | Low | Medium
10 | BUG_HR10 | Future payroll months are displayed as RELEASED before the payroll period. | The Payroll Processing screen displays future payroll months (e.g., August 2026 and October 2026) with a RELEASED status, even though those payroll periods may not have occurred yet. This can mislead users and indicates possible incorrect payroll status handling. | HR & Payroll → Payroll Processing | User is logged into the application. User has access to Payroll Processing. | Navigate to HR & Payroll → Payroll Processing. Open the Previous Runs section. Observe the payroll status of future months. | Future payroll months should not be marked as RELEASED unless payroll has actually been processed and released according to the business rules. | Future payroll months (e.g., August/October 2026) are displayed as RELEASED. | High | High
| BUG_HR10 | Payroll regeneration validation message references a different month than the selected payroll month. | The user selects July 2026 in the Target Month/Year field, but the application displays the message "Payroll for 2026-08 is in RELEASED status and cannot be regenerated." The validation message does not correspond to the selected payroll month, causing confusion. | HR & Payroll → Payroll Processing | User is logged into the application. Payroll records exist. | Open Payroll Processing. Select July 2026 in the Target Month/Year. Click Generate Payroll. Observe the validation message. | The validation message should refer to the selected month (July 2026) or perform the action only for the selected payroll month. | The application displays a validation message for August 2026 instead of the selected month. | High | High
11 | BUG_HR11 | Previous payroll history does not display all processed payroll months. | The Previous Runs section displays only a limited number of payroll months. Earlier payroll history (e.g., May 2026 or older processed payrolls) is not available for viewing, making it difficult for users to access historical payroll records. | HR & Payroll → Payroll Processing | Payroll records exist for previous months. | Navigate to Payroll Processing. View the Previous Runs section. Check whether all historical payroll months are listed. | The application should display all available payroll history or provide pagination/filtering to access older payroll records. | Only a few recent payroll runs are displayed, and earlier payroll history is not accessible. | Medium | Medium
12 | BUG_HR12 | Incorrect approval status displayed when claim is approved by HR | When an HR user approves an employee's claim from the HR portal, the claim status is updated as "Manager Approval" instead of reflecting the correct approval stage. This results in an incorrect workflow status and may confuse users about who approved the claim. | HR & Payroll → Reimbursements Center | User is logged in with HR privileges. An employee claim is submitted and available for approval. The claim is pending HR action. | Log in as an HR user. Navigate to Claims Management. Open a pending employee claim. Click Approve/Accept. Save the action. Observe the updated claim status. | The claim status should display the appropriate HR approval status (e.g., HR Approved, Approved by HR, or the next workflow status as defined in the business requirement). | After HR approves the claim, the status is displayed as Manager Approval, even though the action was performed by the HR user. | High | High

## Manager
S.No | Bug ID | Title/Summary | Description | Module/Screen | Pre-Conditions | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Browser / Device Details | Tested By
1 | MGR-001 | Dashboard UI alignment issues | Multiple cards, widgets and sections are not properly aligned on the dashboard. | Manager → Dashboard | User logged in as Manager. | 1. Login. 2. Open Dashboard. | All dashboard components should be properly aligned. | Multiple UI alignment issues are observed. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
2 | MGR-002 | Dashboard labels do not follow proper capitalization | Menu titles such as Revenue Pipeline, Lead Funnel and Activity Mix are displayed in improper letter case. | Manager → Dashboard | User logged in. | Open Dashboard. | Menu labels should follow consistent capitalization. | Labels appear in inconsistent letter case. | Low | Low | Microsoft Edge/ chrome | Nikhitha
3 | MGR-003 | Executive Overview alignment issues | Several widgets under Executive Overview are misaligned. | Manager → Dashboard | User logged in. | Open Executive Overview. | Widgets should be properly aligned. | Widgets are misaligned. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
4 | MGR-004 | Social Media Account Analytics alignment issues | UI elements in Social Media Account Analytics are not properly aligned. | Manager → Dashboard | User logged in. | Open Dashboard. | UI should be properly aligned. | Alignment issues observed. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
5 | MGR-005 | Left navigation panel scrolls with page | The left navigation panel scrolls together with page content. | Common UI | User logged in. | Scroll any page. | Navigation panel should remain fixed. | Navigation panel scrolls with content. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
6 | MGR-006 | Engagement Trend graph rendering issue | Graph appears distorted and difficult to interpret. | Manager → Campaign Performance | User logged in. | Open Campaign Performance. | Graph should be rendered properly. | Graph appears irregular. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
7 | MGR-007 | Customer Intelligence alignment issues | Customer Satisfaction and Brand Sentiment Score sections are misaligned. | Manager → Customer Intelligence | User logged in. | Open Customer Intelligence. | UI should be properly aligned. | UI alignment issues observed. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
8 | MGR-008 | Rolling Brand Sentiment Trend graph rendering issue | Graph visualization is distorted and difficult to understand. | Manager → Customer Intelligence | User logged in. | View Rolling Brand Sentiment Trend graph. | Graph should render correctly. | Graph appears distorted. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
9 | MGR-009 | Check-in time displayed incorrectly | Check-in records incorrect system time and marks user as late. | Manager → My Attendance | User logged in. | Click Check In. | Current system time should be recorded accurately. | Incorrect check-in time is displayed. | High | High | Microsoft Edge/ chrome | Nikhitha
10 | MGR-010 | My Leaves alignment issues | From Date and To Date fields are misaligned. | Manager → My Leaves | User logged in. | Open My Leaves. | Fields should be aligned. | Alignment issues observed. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
11 | MGR-011 | My Follow-ups alignment issues | Status, From Date and To Date fields are misaligned. | Manager → My Follow-ups | User logged in. | Open My Follow-ups. | Fields should be aligned. | Alignment issues observed. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
12 | MGR-012 | Comment Center alignment issues | Several UI elements are misaligned. | Manager → Monitoring → Comment Center | User logged in. | Open Comment Center. | UI should be aligned. | UI alignment issues observed. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
13 | MGR-013 | Leave Calendar has poor color contrast | Text is difficult to read because of dark/poor color combinations. | Manager → Leave Calendar | User logged in. | Open Leave Calendar. | Text should be clearly visible. | Text visibility is poor. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
14 | MGR-014 | Holiday names wrap incorrectly | Holiday names are split across multiple lines. | Manager → Holidays | User logged in. | Open Holidays. | Holiday names should display properly. | Text wraps incorrectly. | Low | Low | Microsoft Edge/ chrome | Nikhitha
15 | MGR-015 | Attendance Report accepts future dates | Attendance report accepts future dates and displays records without validation. | Manager → Attendance Report | User logged in. | Select future date. | System should prevent future dates. | Future dates are accepted. | Medium | High | Microsoft Edge/ chrome | Nikhitha
16 | MGR-016 | Client Directory alignment issues | Email and Phone Number fields overlap when email is long. | Operations → Client Directory | User logged in. | Open Client Directory. | Columns should remain aligned. | Phone Number shifts due to long email values. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
17 | MGR-017 | Contract date filter accepts unrealistic dates | Contract date filter accepts very old dates (1980/1990) and invalid date ranges. | Operations → Client Directory | User logged in. | Select old/future dates. | System should validate date range. | Invalid dates are accepted. | Medium | High | Microsoft Edge/ chrome | Nikhitha
18 | MGR-018 | Campaign Registry alignment issues | Multiple UI components are misaligned. | Operations → Campaign Registry | User logged in. | Open Campaign Registry. | UI should be aligned. | Alignment issues observed. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
19 | MGR-019 | Content Calendar fields overlap | Month, Week and Date fields overlap each other. | Operations → Content Calendar | User logged in. | Open Content Calendar. | Fields should have proper spacing. | Fields overlap. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
20 | MGR-020 | Schedule Event form lacks input validation | Event Title, Description accept unrestricted special characters and invalid date/time values. | Operations → Content Calendar → Schedule Event | User logged in. | Open Schedule Event and enter invalid data. | System should validate inputs. | Application accepts invalid data. | Medium | High | Microsoft Edge/ chrome | Nikhitha
21 | MGR-021 | Capture Lead accepts invalid First Name and Last Name | First Name and Last Name fields accept identical values without validation. | Lead Manager → Capture Lead | User logged in as Manager. | 1. Navigate to Lead Manager. 2. Click Capture Lead. 3. Enter the same value for First Name and Last Name. 4. Save. | System should validate the entered names based on business rules. | Application accepts identical values without validation. | Low | Medium | Microsoft Edge/ chrome | Nikhitha
22 | MGR-022 | Company Name accepts special characters | Company Name field accepts only special characters without validation. | Lead Manager → Capture Lead | User logged in. | Enter only special characters in Company Name and save. | Company Name should validate the input. | Application accepts invalid Company Name. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
23 | MGR-023 | Email Address accepts invalid email format | Email Address field accepts invalid email formats without validation. | Lead Manager → Capture Lead | User logged in. | Enter an invalid email (e.g., abc@gmail) and save. | System should reject invalid email formats. | Application accepts invalid email addresses. | Medium | High | Microsoft Edge/ chrome | Nikhitha
24 | MGR-024 | Location field accepts special characters | Location field accepts invalid special characters without validation. | Lead Manager → Capture Lead | User logged in. | Enter only special characters in Location. | Location should validate input. | Application accepts invalid Location values. | Low | Medium | Microsoft Edge/ chrome | Nikhitha
25 | MGR-025 | Description field accepts special characters | Description field accepts unrestricted special characters and invalid input. | Lead Manager → Capture Lead | User logged in. | Enter only special characters in Description and save. | Description should validate input according to business rules. | Application accepts invalid Description. | Low | Medium | Microsoft Edge/ chrome | Nikhitha
26 | MGR-026 | Communication Log alignment issues | From Date, To Date and Employee ID fields are misaligned, and some values are partially hidden. | Communications → Communication Log | User logged in. | Open Communication Log. | UI elements should be properly aligned and visible. | Alignment issues and hidden values are observed. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
27 | MGR-027 | Meetings & Demos date/time alignment issue | Date and Time fields are partially hidden due to UI alignment issues. | Communications → Meetings & Demos | User logged in. | Open Meetings & Demos. | Date and Time fields should be properly displayed. | Fields are partially hidden and misaligned. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
28 | MGR-028 | Task Title accepts invalid characters | Task Title field accepts numbers and special characters without validation. | Task Board → Assign Task | User logged in. | Open Assign Task and enter invalid Task Title. | Task Title should validate the input. | Application accepts invalid Task Title. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
29 | MGR-029 | Task Board accepts invalid date range | Assign Task allows future From Date and earlier To Date without validation. | Task Board → Assign Task | User logged in. | Select invalid From Date and To Date. | Application should validate the selected date range. | Application accepts invalid date combinations. | Medium | High | Microsoft Edge/ chrome | Nikhitha
30 | MGR-030 | Task Description accepts special characters | Description field accepts unrestricted special characters without validation. | Task Board → Assign Task | User logged in. | Enter only special characters in Description. | Description should validate the input. | Application accepts invalid Description. | Low | Medium | Microsoft Edge/ chrome | Nikhitha
31 | MGR-031 | Generate Invoice returns 403 error | Generate Invoice action fails and displays a 403 Access Denied error. | Finance → Invoicing | User logged in. | Click Generate Invoice. | Invoice should be generated successfully. | Application displays a 403 Access Denied error. | High | High | Microsoft Edge/ chrome | Nikhitha
32 | MGR-032 | Invoice Status filter is incomplete | Status dropdown displays only Unpaid and Overdue options. | Finance → Invoicing | User logged in. | Click Status filter. | All configured invoice statuses should be displayed. | Only Unpaid and Overdue are displayed. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
33 | MGR-033 | Marketing page UI alignment issues | Marketing page contains inconsistent fonts, colors, spacing and alignment. | Marketing → Campaign Performance | User logged in. | Open Campaign Performance. | UI should be consistent across the page. | Multiple UI inconsistencies are observed. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
34 | MGR-034 | Update Social Stats returns 403 Access Denied | Update Social Stats module cannot be accessed due to a 403 Access Denied error. | Marketing → Update Social Stats | User logged in. | Open Update Social Stats. | Page should load successfully. | Application displays 403 Access Denied. | High | High | Microsoft Edge/ chrome | Nikhitha
35 | MGR-035 | Reports page alignment issues | From Date, To Date and filter controls are misaligned, with some fields partially hidden. | Reports | User logged in. | Open Reports. | All filter controls should be properly aligned. | Several fields are misaligned. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
36 | MGR-036 | Reports module accepts invalid date range | Reports module accepts future From Date and earlier To Date without validation. | Reports | User logged in. | Select an invalid date range. | System should validate the selected dates. | Application accepts invalid date combinations. | Medium | High | Microsoft Edge/ chrome | Nikhitha
37 | MGR-037 | Organization module displays Access Denied | Organization module cannot be accessed and displays an Access Denied error. | HR & Payroll → Organization | User logged in as Manager. | Open Organization module. | Organization page should load successfully. | Application displays Access Denied. | High | High | Microsoft Edge/ chrome | Nikhitha
38 | MGR-038 | HR Dashboard has poor color contrast and alignment issues | Several dashboard cards, holiday section and widgets have poor color contrast and alignment issues, making content difficult to read. | HR & Payroll → HR Dashboard | User logged in. | Open HR Dashboard. | Dashboard should have proper alignment and readable colors. | Content is difficult to read due to poor colors and alignment issues. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
39 | MGR-039 | Future payroll months displayed as Released | Payroll Dashboard displays future payroll months with Released status before the payroll period. | HR & Payroll → Payroll Dashboard | User logged in. | Open Payroll Dashboard and observe payroll runs. | Future payroll months should not appear as Released unless processed according to business rules. | Future payroll months are displayed with Released status. | High | High | Microsoft Edge/ chrome | Nikhitha
40 | MGR-040 | Reimbursement page has poor UI visibility | Reimbursement page contains poor color contrast, alignment issues and partially hidden fields. | HR & Payroll → Reimbursement | User logged in. | Open Reimbursement module. | All UI elements should be properly aligned and clearly visible. | Multiple UI elements are difficult to read due to poor colors and alignment issues. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha

## Analyst
S.No | Bug ID | Title/Summary | Description | Module/Screen | Pre-Conditions | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Browser / Device Details | Tested By
1 | ANL-001 | UI alignment issues on Dashboard | Multiple UI components, cards, widgets, and sections on the Dashboard are misaligned, affecting the overall appearance and usability. | Analyst → Dashboard | User logged in as Analyst. | 1. Login as Analyst. 2. Navigate to Dashboard. 3. Observe the page layout. | All dashboard components should be properly aligned and consistently displayed. | Several UI elements are misaligned, making the dashboard appear unorganized. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
2 | ANL-002 | Dashboard and Dashboard Template menus remain selected simultaneously | When Dashboard Template is selected, both Dashboard and Dashboard Template remain highlighted, causing incorrect navigation indication. | Analyst → Navigation | User logged in as Analyst. | 1. Open Dashboard. 2. Click Dashboard Template. | Only the selected menu should remain highlighted. | Both Dashboard and Dashboard Template appear selected simultaneously. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
3 | ANL-003 | Template Name field accepts invalid characters | The Template Name field accepts special characters, numbers, and unrestricted input without validation. | Analyst → Dashboard Template | User is on Dashboard Template page. | 1. Click Create Dashboard Template. 2. Enter special characters or invalid values in Template Name. 3. Save. | Template Name should validate input according to business rules. | The field accepts invalid characters without validation. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
4 | ANL-004 | Description field lacks input validation | The Description field accepts unrestricted input without validation or defined limits. | Analyst → Dashboard Template | User is on Dashboard Template page. | 1. Enter random/special characters in Description. 2. Save. | Description field should validate input based on business requirements. | Application accepts unrestricted input. | Low | Medium | Microsoft Edge/ chrome | Nikhitha
5 | ANL-005 | Base Dashboard dropdown text is partially hidden | Selected values in the Base Dashboard dropdown are partially hidden due to UI alignment issues. | Analyst → Dashboard Template | User is on Dashboard Template page. | 1. Open Base Dashboard dropdown. 2. Select a value. | The selected value should be fully visible. | The selected value is partially hidden. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
6 | ANL-006 | Engagement Trend graph rendering issue | The Engagement Trend graph appears distorted and irregular, making it difficult to interpret the data accurately. | Analyst → Company Performance | User is on Company Performance page. | 1. Navigate to Company Performance. 2. View Engagement Trend graph. | Graph should be rendered smoothly with proper visualization. | The graph appears irregular and visually distorted. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
7 | ANL-007 | Poor color contrast in Engagement Trend graph | The colors used in the Engagement Trend graph reduce readability and make the data difficult to interpret. | Analyst → Company Performance | User is on Company Performance page. | 1. Navigate to Company Performance. 2. Observe graph colors. | Graph colors should provide sufficient contrast for readability. | Graph colors are difficult to distinguish and affect readability. | Low | Medium | Microsoft Edge/ chrome | Nikhitha
8 | ANL-008 | UI alignment issues in Customer Intelligence cards | Cards and widgets inside Customer Intelligence have inconsistent sizes and alignment. | Analyst → Customer Intelligence | User is on Customer Intelligence page. | 1. Navigate to Customer Intelligence. 2. Observe cards and widgets. | All cards should have consistent alignment and sizing. | Several cards appear misaligned and inconsistent in size. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
9 | ANL-009 | Rolling Brand Sentiment Trend graph rendering issue | The Rolling Brand Sentiment Trend graph appears irregular and visually inconsistent. | Analyst → Customer Intelligence | User is on Customer Intelligence page. | 1. Open Customer Intelligence. 2. Observe Rolling Brand Sentiment Trend graph. | Graph should display smooth and accurate visualization. | Graph appears distorted and difficult to interpret. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
10 | ANL-010 | Poor color contrast in Rolling Brand Sentiment Trend graph | The graph uses poor color combinations, reducing readability of the displayed data. | Analyst → Customer Intelligence | User is on Customer Intelligence page. | 1. Open Customer Intelligence. 2. Observe graph colors. | Graph colors should provide clear visibility. | Colors make graph data difficult to read. | Low | Medium | Microsoft Edge/ chrome | Nikhitha
11 | ANL-011 | Multiple UI alignment issues across Customer Intelligence page | Several UI elements throughout the Customer Intelligence page are misaligned. | Analyst → Customer Intelligence | User is on Customer Intelligence page. | 1. Navigate to Customer Intelligence. 2. Observe the page. | All UI components should be properly aligned. | Multiple alignment issues are observed throughout the page. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
12 | ANL-012 | Updates Social Stats displays 403 Access Denied | The Updates Social Stats page cannot be accessed and displays a 403 Access Denied error. | Analyst → Updates Social Stats | User logged in as Analyst. | 1. Navigate to Updates Social Stats. | Module should open successfully. | Application displays 403 Access Denied. | High | High | Microsoft Edge/ chrome | Nikhitha
13 | ANL-013 | Reports page has UI alignment issues | The From Date, To Date, and other UI elements are misaligned, with some text partially hidden. | Analyst → Reports | User is on Reports page. | 1. Navigate to Reports. 2. Observe filter section. | All fields should be properly aligned and visible. | Several fields are misaligned and partially hidden. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
14 | ANL-014 | Reports module accepts invalid date range | The Reports module allows selecting a future From Date and an earlier To Date without validation. | Analyst → Reports | User is on Reports page. | 1. Select future From Date. 2. Select earlier To Date. 3. Apply filter. | Application should validate the date range before applying filters. | Application accepts invalid date combinations. | Medium | High | Microsoft Edge/ chrome | Nikhitha
15 | ANL-015 | Left navigation panel scrolls with page | The left navigation panel scrolls together with the page content instead of remaining fixed. | Common UI | User logged into the application. | 1. Open any long page. 2. Scroll down. | Left navigation should remain fixed while content scrolls. | The navigation panel scrolls together with the page. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha

## Finance
S.No | Bug ID | Title/Summary | Description | Module/Screen | Pre-Conditions | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Browser / Device Details | Tested By
1 | FIN-001 | Finance Dashboard displays blank page | Finance Dashboard loads without displaying any widgets, charts, or dashboard data. | Finance → Dashboard | User logged in as Finance. | 1. Login as Finance user. 2. Navigate to Dashboard. | The dashboard should display relevant financial widgets, charts, and information. | The dashboard opens as a blank page with no data displayed. | High | High | Microsoft Edge/ chrome | Nikhitha
2 | FIN-002 | My Attendance shows 403 Access Denied | Finance user receives a 403 Access Denied error while opening My Attendance. | My Day → My Attendance | User logged in as Finance. | 1. Login. 2. Navigate to My Day → My Attendance. | My Attendance page should open successfully based on user permissions. | Application displays "403 Access Denied" and redirects to Home. | High | High | Microsoft Edge/ chrome | Nikhitha
3 | FIN-003 | UI alignment issues in My Leaves | Multiple UI alignment issues are observed in the My Leaves page. Labels, date fields, and UI components are misaligned. | My Day → My Leaves | User logged in. | 1. Navigate to My Day → My Leaves. 2. Observe the page layout. | All UI components should be properly aligned. | Several UI elements are misaligned. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
4 | FIN-004 | My Leaves accepts invalid date range | The From Date and To Date fields allow invalid date combinations without validation. | My Day → My Leaves | User logged in. | 1. Select a future From Date. 2. Select an earlier To Date. 3. Apply filter. | System should validate the date range and prevent invalid selections. | Application accepts invalid date combinations. | Medium | High | Microsoft Edge/ chrome | Nikhitha
5 | FIN-005 | UI alignment issues in My Follow-ups | Status labels and date fields are misaligned, affecting readability. | My Day → My Follow-ups | User logged in. | 1. Navigate to My Follow-ups. 2. Observe Status, From Date, and To Date fields. | All fields should be properly aligned. | Status text and date fields are misaligned. | Low | Medium | Microsoft Edge/ chrome | Nikhitha
6 | FIN-006 | Generate Invoice returns 404 error | Clicking Generate Invoice fails and displays a 404 Not Found error. | Finance → Invoice | User logged in as Finance. | 1. Navigate to Finance → Invoice. 2. Click Generate Invoice. | Invoice should be generated successfully. | Application displays 404 Not Found error. | High | High | Microsoft Edge/ chrome | Nikhitha
7 | FIN-007 | Invoice Status filter hides available options | Status dropdown displays only Unpaid while other status options are unavailable. | Finance → Invoice | User logged in. | 1. Open Invoice page. 2. Click Status dropdown. | Status dropdown should display all available statuses. | Only Unpaid option is visible. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
8 | FIN-008 | Invoice accepts invalid date range | Date filters allow invalid combinations such as future From Date and past To Date. | Finance → Invoice | User logged in. | 1. Select invalid date range. 2. Apply filter. | System should validate date selection. | Application accepts invalid date combinations. | Medium | High | Microsoft Edge/ chrome | Nikhitha
9 | FIN-009 | Invoice page has date field alignment issues | From Date and To Date fields are not properly aligned. | Finance → Invoice | User logged in. | 1. Open Invoice page. 2. Observe date fields. | Date fields should be properly aligned. | Date fields are misaligned. | Low | Medium | Microsoft Edge/ chrome | Nikhitha
10 | FIN-010 | Analytics History returns 404 error | Opening Analytics History results in a 404 Not Found error. | Finance → Analytics History | User logged in. | 1. Navigate to Analytics History. | Analytics History should load successfully. | Application displays 404 Not Found error. | High | High | Microsoft Edge/ chrome | Nikhitha
11 | FIN-011 | Poor color contrast in Add Claim popup | Add Claim popup uses poor color combinations, making text difficult to read. | HR & Payroll → Reimbursement → Add Claim | User logged in as Finance. | 1. Navigate to Reimbursement. 2. Click Claim Now → Add Claim. | All labels and fields should be clearly visible. | Text and labels are difficult to read due to poor color contrast. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
12 | FIN-012 | Allocate Bonus selection is not properly highlighted | Selected employee/status is not clearly highlighted due to poor color contrast. | HR & Payroll → Bonus → Allocate Bonus | User logged in. | 1. Navigate to Allocate Bonus. 2. Select an employee. | Selected employee should be clearly highlighted. | Selected row/status is displayed in light white color and is difficult to identify. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
13 | FIN-013 | Left navigation panel scrolls with page | The left navigation menu scrolls together with page content instead of remaining fixed. | Common UI / Navigation | User logged in. | 1. Open any scrollable page. 2. Scroll down. | Left navigation should remain fixed while content scrolls. | Navigation panel scrolls together with the page. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha

## Employee
S.No | Bug ID | Title/Summary | Description | Module/Screen | Pre-Conditions | Steps to reproduce | Expected Result | Actual Result | Severity | Priority | Browser / Device Details | Tested By
1 | BUG_001 | Application allows users to reuse their old password as the new password during password reset. | During the password reset process, the application allows users to set their new password to the same password that is currently associated with their account. This defeats the purpose of a password reset and does not enforce password security best practices. The system should validate that the new password is different from the existing password before allowing the reset. | Authentication → Forgot Password / Reset Password | 1. User has a registered and active account. 2. User knows the current password. 3. Forgot Password functionality is enabled. 4. User has access to the registered email/OTP required to verify identity. | 1. Open the application login page. 2. Click on Forgot Password?. 3. Enter a registered email address and complete the verification process (OTP or email link). 4. Navigate to the Reset Password page. 5. Enter the same password that is currently being used as the New Password. 6. Re-enter the same password in the Confirm Password field. 7. Click Reset/Submit. 8. Observe the result. | The application should reject the password reset request and display a validation message such as "New password cannot be the same as your current password. Please choose a different password." The password should not be updated. | The application accepts the current/old password as the new password and successfully completes the password reset without displaying any validation message. | High | High | Microsoft Edge/ chrome | Nikhitha
2 | BUG_002 | Incorrect check-in time is displayed after successful Clock In/Check-In. | When a user performs a Clock In/Check-In, the attendance is successfully recorded. However, the system displays an incorrect check-in time that does not match the actual local time. This creates inaccurate attendance records and may impact employee working hours and payroll calculations. | Attendance Management → Clock In / Check-In | 1. User is logged into the Attendance Portal. 2. User is eligible to perform Clock In/Check-In. 3. Internet connection is stable. 4. System date and time on the user's device are correct. | 1. Log in to the Attendance Portal. 2. Navigate to the Attendance page. 3. Click on Clock In or Check-In. 4. Observe the time displayed after the check-in is completed. 5. Compare the displayed check-in time with the actual current local time. | The system should record and display the actual local time at which the user clicked Clock In/Check-In. For example, if the user checks in at 11:27 AM, the attendance record should display 11:27 AM. | Although the check-in is successful, the system displays an incorrect time. For example, when the user checks in at 11:27 AM, the attendance record displays 5:47 AM, resulting in an inaccurate attendance timestamp. | High (Incorrect attendance time can affect attendance records, working hours, payroll calculations, and reporting.) | High | Microsoft Edge/ chrome | Nikhitha
3 | BUG-003 | Reset Password accepts the current password as the new password | During the password reset process, the application allows the user to set the current (old) password again as the new password. This defeats the purpose of password reset and weakens password security. | Login → Forgot Password / Reset Password | User has a valid account and has reached the Reset Password page through the Forgot Password flow. | 1. Navigate to the Login page. 2. Click Forgot Password. 3. Complete the verification process. 4. On the Reset Password page, enter the current password in the New Password field. 5. Confirm the same password and submit. | The application should reject the current password as the new password and display an appropriate validation message such as "New password cannot be the same as the current password." | The application accepts the current password as the new password and updates it successfully. | High | High | Microsoft Edge/ chrome | Nikhitha
4 | BUG-004 | Check-in records incorrect system time | When the employee clicks the Check In button, the application records and displays an incorrect check-in time, which may also affect attendance status. | My Day → My Attendance | User is logged in as Employee. | 1. Login as Employee. 2. Navigate to My Day → My Attendance. 3. Click Check In. 4. Observe the recorded time. | The application should record and display the actual current system time during check-in. | The application records and displays an incorrect check-in time. | High | High | Microsoft Edge/ chrome | Nikhitha
5 | BUG-005 | My Follow-ups status and Target Due Date alignment issues | The Status and Target Due Date fields are misaligned, causing some values to be partially hidden and difficult to read. | My Day → My Follow-ups | User is logged in as Employee. | 1. Login as Employee. 2. Navigate to My Day → My Follow-ups. 3. Observe the Status and Target Due Date fields. | Status and Target Due Date fields should be properly aligned and completely visible. | Status and Target Due Date fields are misaligned and partially hidden. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
6 | BUG-006 | My Route displays incorrect location | The My Route module displays an incorrect location that does not match the employee's actual location or assigned route. | My Route | User is logged in as Employee. | 1. Login as Employee. 2. Navigate to My Route. 3. Observe the displayed route/location. | The application should display the correct route/location. | The application displays an incorrect location. | High | High | Microsoft Edge/ chrome | Nikhitha
7 | BUG-007 | Location Stats displays Access Denied | Clicking on the Location Stats option results in an Access Denied error, preventing the user from accessing the page. | My Route → Location Stats | User is logged in as Employee. | 1. Login as Employee. 2. Navigate to My Route. 3. Click on Location Stats. | The Location Stats page should open successfully for authorized users. | The application displays an Access Denied error. | High | High | Microsoft Edge/ chrome | Nikhitha
8 | BUG-008 | HR Dashboard has poor color contrast and alignment issues | The HR Dashboard contains poor color combinations, hidden text, and multiple alignment issues, making the dashboard difficult to read and use. | HR & Payroll → HR Dashboard | User is logged in as Employee. | 1. Login as Employee. 2. Navigate to HR Dashboard. 3. Observe the dashboard layout and colors. | The dashboard should have proper alignment, readable colors, and all information should be clearly visible. | The dashboard contains poor color contrast, hidden text, and multiple alignment issues. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha
9 | BUG-009 | HR Payroll page has color and alignment issues | The HR Payroll page contains poor color combinations, hidden fields, and multiple alignment issues that affect readability and usability. | HR & Payroll | User is logged in as Employee. | 1. Login as Employee. 2. Navigate to HR & Payroll. 3. Observe the page layout. | All fields should be properly aligned, clearly visible, and use readable color combinations. | Several fields are hidden due to poor color contrast, and multiple alignment issues are observed. | Medium | Medium | Microsoft Edge/ chrome | Nikhitha